## Master Gap Tracker
Gap ID | Module | Industry | Gap Title | Classification | Current Status | Current Behavior | Expected Behavior | Competitor | Competitor Feature | Evidence URL | Evidence Date | Evidence Confidence | Business Impact | User Pain | Competitive Importance | Estimated Effort | Priority | Proposed Solution | Dependencies | Acceptance Criteria | QA Scenarios | Research Status | Notes
HGC-GAP-0018 | Real Estate | Real Estate | Real Estate Temporary Unit Holding Lock (30-Min Token Hold) | INDUSTRY GAP | VERIFIED DEFECT / GAP | Verified current state in Real Estate: functionality missing, partial, or unoptimized. | Implementation of Real Estate Temporary Unit Holding Lock (30-Min Token Hold) according to global SaaS benchmarks. | Specialist Real Estate CRMs | Benchmark equivalent for Real Estate Temporary Unit Holding Lock (30-Min Token Hold) | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 5 | 5 | Small (1 wk) | P0 | Implement Real Estate Temporary Unit Holding Lock (30-Min Token Hold) per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Real Estate Temporary Unit Holding Lock (30-Min Token Hold) with zero regression. | Automated integration tests and UI verification for HGC-GAP-0018 | Validated | Calculated Opportunity Score: 5.0
HGC-GAP-0022 | Retail / POS | Retail | WebUSB/WebSerial Direct ESC/POS Thermal Receipt Printing | HARDWARE GAP | VERIFIED DEFECT / GAP | Verified current state in Retail / POS: functionality missing, partial, or unoptimized. | Implementation of WebUSB/WebSerial Direct ESC/POS Thermal Receipt Printing according to global SaaS benchmarks. | Specialist Retail CRMs | Benchmark equivalent for WebUSB/WebSerial Direct ESC/POS Thermal Receipt Printing | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 5 | 4 | Medium (2 wks) | P0 | Implement WebUSB/WebSerial Direct ESC/POS Thermal Receipt Printing per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of WebUSB/WebSerial Direct ESC/POS Thermal Receipt Printing with zero regression. | Automated integration tests and UI verification for HGC-GAP-0022 | Validated | Calculated Opportunity Score: 4.65
HGC-GAP-0044 | Database & Perf | Horizontal | Compound B-Tree Indexes on High-Traffic Webhook & Activity Tables | PERFORMANCE GAP | VERIFIED DEFECT / GAP | Verified current state in Database & Perf: functionality missing, partial, or unoptimized. | Implementation of Compound B-Tree Indexes on High-Traffic Webhook & Activity Tables according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Compound B-Tree Indexes on High-Traffic Webhook & Activity Tables | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 5 | 4 | Small (1 day) | P0 | Implement Compound B-Tree Indexes on High-Traffic Webhook & Activity Tables per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Compound B-Tree Indexes on High-Traffic Webhook & Activity Tables with zero regression. | Automated integration tests and UI verification for HGC-GAP-0044 | Validated | Calculated Opportunity Score: 4.45
HGC-GAP-0010 | Security & Admin | Horizontal | Supabase Currency Settings Write Permission Vulnerability | SECURITY GAP | VERIFIED DEFECT / GAP | Verified current state in Security & Admin: functionality missing, partial, or unoptimized. | Implementation of Supabase Currency Settings Write Permission Vulnerability according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Supabase Currency Settings Write Permission Vulnerability | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 5 | 4 | Small (1 day) | P0 | Implement Supabase Currency Settings Write Permission Vulnerability per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Supabase Currency Settings Write Permission Vulnerability with zero regression. | Automated integration tests and UI verification for HGC-GAP-0010 | Validated | Calculated Opportunity Score: 4.25
HGC-GAP-0024 | CA & Accounting | Accounting | Government GSTN / Income Tax GSP Live Portal Status Sync | INTEGRATION GAP | VERIFIED DEFECT / GAP | Verified current state in CA & Accounting: functionality missing, partial, or unoptimized. | Implementation of Government GSTN / Income Tax GSP Live Portal Status Sync according to global SaaS benchmarks. | Specialist Accounting CRMs | Benchmark equivalent for Government GSTN / Income Tax GSP Live Portal Status Sync | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 5 | 5 | Large (3 wks) | P1 | Implement Government GSTN / Income Tax GSP Live Portal Status Sync per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Government GSTN / Income Tax GSP Live Portal Status Sync with zero regression. | Automated integration tests and UI verification for HGC-GAP-0024 | Validated | Calculated Opportunity Score: 5.0
HGC-GAP-0017 | Insurance | Insurance | Automated Policy Renewal Instant WhatsApp Payment Bot | AUTOMATION GAP | VERIFIED DEFECT / GAP | Verified current state in Insurance: functionality missing, partial, or unoptimized. | Implementation of Automated Policy Renewal Instant WhatsApp Payment Bot according to global SaaS benchmarks. | Specialist Insurance CRMs | Benchmark equivalent for Automated Policy Renewal Instant WhatsApp Payment Bot | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 4 | 5 | Medium (2 wks) | P1 | Implement Automated Policy Renewal Instant WhatsApp Payment Bot per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Automated Policy Renewal Instant WhatsApp Payment Bot with zero regression. | Automated integration tests and UI verification for HGC-GAP-0017 | Validated | Calculated Opportunity Score: 4.8
HGC-GAP-0023 | Retail / POS | Retail | Offline Cash Register Fallback with Local IndexedDB Sync | PERFORMANCE GAP | VERIFIED DEFECT / GAP | Verified current state in Retail / POS: functionality missing, partial, or unoptimized. | Implementation of Offline Cash Register Fallback with Local IndexedDB Sync according to global SaaS benchmarks. | Specialist Retail CRMs | Benchmark equivalent for Offline Cash Register Fallback with Local IndexedDB Sync | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 5 | 5 | Large (3 wks) | P1 | Implement Offline Cash Register Fallback with Local IndexedDB Sync per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Offline Cash Register Fallback with Local IndexedDB Sync with zero regression. | Automated integration tests and UI verification for HGC-GAP-0023 | Validated | Calculated Opportunity Score: 4.8
HGC-GAP-0028 | Agri / Field Sales | Field Sales | Automated TSP Beat Route Sequencing for Rural Dealer Reps | MARKET DIFFERENTIATION OPPORTUNITY | VERIFIED DEFECT / GAP | Verified current state in Agri / Field Sales: functionality missing, partial, or unoptimized. | Implementation of Automated TSP Beat Route Sequencing for Rural Dealer Reps according to global SaaS benchmarks. | Specialist Field Sales CRMs | Benchmark equivalent for Automated TSP Beat Route Sequencing for Rural Dealer Reps | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 5 | 5 | Medium (2 wks) | P1 | Implement Automated TSP Beat Route Sequencing for Rural Dealer Reps per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Automated TSP Beat Route Sequencing for Rural Dealer Reps with zero regression. | Automated integration tests and UI verification for HGC-GAP-0028 | Validated | Calculated Opportunity Score: 4.8
HGC-GAP-0032 | Digital Agencies | Agencies | Custom Domain White-Label Portal Sub-Tenancy | MARKET DIFFERENTIATION OPPORTUNITY | VERIFIED DEFECT / GAP | Verified current state in Digital Agencies: functionality missing, partial, or unoptimized. | Implementation of Custom Domain White-Label Portal Sub-Tenancy according to global SaaS benchmarks. | Specialist Agencies CRMs | Benchmark equivalent for Custom Domain White-Label Portal Sub-Tenancy | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 4 | 5 | Medium (2 wks) | P1 | Implement Custom Domain White-Label Portal Sub-Tenancy per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Custom Domain White-Label Portal Sub-Tenancy with zero regression. | Automated integration tests and UI verification for HGC-GAP-0032 | Validated | Calculated Opportunity Score: 4.8
HGC-GAP-0027 | Manufacturing | Manufacturing | Raw Material Stock Shortage Alert on Work Order Release | AUTOMATION GAP | VERIFIED DEFECT / GAP | Verified current state in Manufacturing: functionality missing, partial, or unoptimized. | Implementation of Raw Material Stock Shortage Alert on Work Order Release according to global SaaS benchmarks. | Specialist Manufacturing CRMs | Benchmark equivalent for Raw Material Stock Shortage Alert on Work Order Release | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 5 | 4 | Medium (2 wks) | P1 | Implement Raw Material Stock Shortage Alert on Work Order Release per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Raw Material Stock Shortage Alert on Work Order Release with zero regression. | Automated integration tests and UI verification for HGC-GAP-0027 | Validated | Calculated Opportunity Score: 4.65
HGC-GAP-0001 | Sales Pipeline | Horizontal | Enforced Pipeline Stage Gating & Required Stage Fields | AUTOMATION GAP | VERIFIED DEFECT / GAP | Verified current state in Sales Pipeline: functionality missing, partial, or unoptimized. | Implementation of Enforced Pipeline Stage Gating & Required Stage Fields according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Enforced Pipeline Stage Gating & Required Stage Fields | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 4 | 4 | Medium (2-3 wks) | P1 | Implement Enforced Pipeline Stage Gating & Required Stage Fields per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Enforced Pipeline Stage Gating & Required Stage Fields with zero regression. | Automated integration tests and UI verification for HGC-GAP-0001 | Validated | Calculated Opportunity Score: 4.45
HGC-GAP-0029 | Agri / Field Sales | Field Sales | Distributor Overdue Credit Limit Gate Blocking New Orders | AUTOMATION GAP | VERIFIED DEFECT / GAP | Verified current state in Agri / Field Sales: functionality missing, partial, or unoptimized. | Implementation of Distributor Overdue Credit Limit Gate Blocking New Orders according to global SaaS benchmarks. | Specialist Field Sales CRMs | Benchmark equivalent for Distributor Overdue Credit Limit Gate Blocking New Orders | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 5 | 4 | Small (1 wk) | P1 | Implement Distributor Overdue Credit Limit Gate Blocking New Orders per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Distributor Overdue Credit Limit Gate Blocking New Orders with zero regression. | Automated integration tests and UI verification for HGC-GAP-0029 | Validated | Calculated Opportunity Score: 4.45
HGC-GAP-0015 | Education / Coaching | Education | Automated Overdue Fee Installment WhatsApp Drip Bot | AUTOMATION GAP | VERIFIED DEFECT / GAP | Verified current state in Education / Coaching: functionality missing, partial, or unoptimized. | Implementation of Automated Overdue Fee Installment WhatsApp Drip Bot according to global SaaS benchmarks. | Specialist Education CRMs | Benchmark equivalent for Automated Overdue Fee Installment WhatsApp Drip Bot | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 5 | 4 | Small (1 wk) | P1 | Implement Automated Overdue Fee Installment WhatsApp Drip Bot per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Automated Overdue Fee Installment WhatsApp Drip Bot with zero regression. | Automated integration tests and UI verification for HGC-GAP-0015 | Validated | Calculated Opportunity Score: 4.4
HGC-GAP-0040 | AI & MCP | Horizontal | Official Model Context Protocol (MCP) Registry Listing | INTEGRATION GAP | VERIFIED DEFECT / GAP | Verified current state in AI & MCP: functionality missing, partial, or unoptimized. | Implementation of Official Model Context Protocol (MCP) Registry Listing according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Official Model Context Protocol (MCP) Registry Listing | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 3 | 5 | Small (2 days) | P1 | Implement Official Model Context Protocol (MCP) Registry Listing per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Official Model Context Protocol (MCP) Registry Listing with zero regression. | Automated integration tests and UI verification for HGC-GAP-0040 | Validated | Calculated Opportunity Score: 4.4
HGC-GAP-0041 | AI & MCP | Horizontal | Standardized search/fetch Primitive Tools for HGC MCP Server | FEATURE GAP | VERIFIED DEFECT / GAP | Verified current state in AI & MCP: functionality missing, partial, or unoptimized. | Implementation of Standardized search/fetch Primitive Tools for HGC MCP Server according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Standardized search/fetch Primitive Tools for HGC MCP Server | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 5 | 4 | 4 | Small (3 days) | P1 | Implement Standardized search/fetch Primitive Tools for HGC MCP Server per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Standardized search/fetch Primitive Tools for HGC MCP Server with zero regression. | Automated integration tests and UI verification for HGC-GAP-0041 | Validated | Calculated Opportunity Score: 4.25
HGC-GAP-0014 | Education / Coaching | Education | Hardware Biometric Device API Sync (ZKTeco/Essl) | INTEGRATION GAP | VERIFIED DEFECT / GAP | Verified current state in Education / Coaching: functionality missing, partial, or unoptimized. | Implementation of Hardware Biometric Device API Sync (ZKTeco/Essl) according to global SaaS benchmarks. | Specialist Education CRMs | Benchmark equivalent for Hardware Biometric Device API Sync (ZKTeco/Essl) | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Medium (2 wks) | P1 | Implement Hardware Biometric Device API Sync (ZKTeco/Essl) per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Hardware Biometric Device API Sync (ZKTeco/Essl) with zero regression. | Automated integration tests and UI verification for HGC-GAP-0014 | Validated | Calculated Opportunity Score: 4.2
HGC-GAP-0021 | Travel Agencies | Travel | Offline Mobile Traveler Itinerary PWA Caching | FEATURE GAP | VERIFIED DEFECT / GAP | Verified current state in Travel Agencies: functionality missing, partial, or unoptimized. | Implementation of Offline Mobile Traveler Itinerary PWA Caching according to global SaaS benchmarks. | Specialist Travel CRMs | Benchmark equivalent for Offline Mobile Traveler Itinerary PWA Caching | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Small (1 wk) | P1 | Implement Offline Mobile Traveler Itinerary PWA Caching per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Offline Mobile Traveler Itinerary PWA Caching with zero regression. | Automated integration tests and UI verification for HGC-GAP-0021 | Validated | Calculated Opportunity Score: 4.2
HGC-GAP-0037 | UI/UX & Shell | Horizontal | Sticky Left Column Pinning in Responsive Wide Data Tables | UI/UX IMPROVEMENT | VERIFIED DEFECT / GAP | Verified current state in UI/UX & Shell: functionality missing, partial, or unoptimized. | Implementation of Sticky Left Column Pinning in Responsive Wide Data Tables according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Sticky Left Column Pinning in Responsive Wide Data Tables | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 5 | 4 | Small (3 days) | P1 | Implement Sticky Left Column Pinning in Responsive Wide Data Tables per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Sticky Left Column Pinning in Responsive Wide Data Tables with zero regression. | Automated integration tests and UI verification for HGC-GAP-0037 | Validated | Calculated Opportunity Score: 4.2
HGC-GAP-0038 | UI/UX & Shell | Horizontal | Interactive Demo Sample Records Button on Empty State Views | UI/UX IMPROVEMENT | VERIFIED DEFECT / GAP | Verified current state in UI/UX & Shell: functionality missing, partial, or unoptimized. | Implementation of Interactive Demo Sample Records Button on Empty State Views according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Interactive Demo Sample Records Button on Empty State Views | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Small (1 wk) | P1 | Implement Interactive Demo Sample Records Button on Empty State Views per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Interactive Demo Sample Records Button on Empty State Views with zero regression. | Automated integration tests and UI verification for HGC-GAP-0038 | Validated | Calculated Opportunity Score: 4.2
HGC-GAP-0002 | Quotes & Commerce | Horizontal | Server-Side Discount Approval Thresholds (>15%) | AUTOMATION GAP | VERIFIED DEFECT / GAP | Verified current state in Quotes & Commerce: functionality missing, partial, or unoptimized. | Implementation of Server-Side Discount Approval Thresholds (>15%) according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Server-Side Discount Approval Thresholds (>15%) | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Medium (2 wks) | P1 | Implement Server-Side Discount Approval Thresholds (>15%) per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Server-Side Discount Approval Thresholds (>15%) with zero regression. | Automated integration tests and UI verification for HGC-GAP-0002 | Validated | Calculated Opportunity Score: 4.0
HGC-GAP-0003 | Lead Management | Horizontal | Fuzzy & Probabilistic Lead Deduplication Engine | FEATURE GAP | VERIFIED DEFECT / GAP | Verified current state in Lead Management: functionality missing, partial, or unoptimized. | Implementation of Fuzzy & Probabilistic Lead Deduplication Engine according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Fuzzy & Probabilistic Lead Deduplication Engine | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 5 | 4 | Medium (2 wks) | P1 | Implement Fuzzy & Probabilistic Lead Deduplication Engine per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Fuzzy & Probabilistic Lead Deduplication Engine with zero regression. | Automated integration tests and UI verification for HGC-GAP-0003 | Validated | Calculated Opportunity Score: 4.0
HGC-GAP-0006 | Customer Support | Horizontal | Cross-Channel Conversation Thread Auto-Merging (WA + Email + Portal) | FEATURE GAP | VERIFIED DEFECT / GAP | Verified current state in Customer Support: functionality missing, partial, or unoptimized. | Implementation of Cross-Channel Conversation Thread Auto-Merging (WA + Email + Portal) according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Cross-Channel Conversation Thread Auto-Merging (WA + Email + Portal) | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 5 | 4 | Medium (2 wks) | P1 | Implement Cross-Channel Conversation Thread Auto-Merging (WA + Email + Portal) per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Cross-Channel Conversation Thread Auto-Merging (WA + Email + Portal) with zero regression. | Automated integration tests and UI verification for HGC-GAP-0006 | Validated | Calculated Opportunity Score: 4.0
HGC-GAP-0012 | Healthcare / Clinic | Healthcare | Diagnostic Lab Report & DICOM/HL7 Attachment Parsing | INDUSTRY GAP | VERIFIED DEFECT / GAP | Verified current state in Healthcare / Clinic: functionality missing, partial, or unoptimized. | Implementation of Diagnostic Lab Report & DICOM/HL7 Attachment Parsing according to global SaaS benchmarks. | Specialist Healthcare CRMs | Benchmark equivalent for Diagnostic Lab Report & DICOM/HL7 Attachment Parsing | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Large (3 wks) | P1 | Implement Diagnostic Lab Report & DICOM/HL7 Attachment Parsing per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Diagnostic Lab Report & DICOM/HL7 Attachment Parsing with zero regression. | Automated integration tests and UI verification for HGC-GAP-0012 | Validated | Calculated Opportunity Score: 4.0
HGC-GAP-0009 | Payments & Billing | Horizontal | PayU Payment Gateway Discrepancy (Backend Missing) | FUNCTIONAL BUG | VERIFIED DEFECT / GAP | Verified current state in Payments & Billing: functionality missing, partial, or unoptimized. | Implementation of PayU Payment Gateway Discrepancy (Backend Missing) according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for PayU Payment Gateway Discrepancy (Backend Missing) | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 3 | 4 | Small (3 days) | P1 | Implement PayU Payment Gateway Discrepancy (Backend Missing) per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of PayU Payment Gateway Discrepancy (Backend Missing) with zero regression. | Automated integration tests and UI verification for HGC-GAP-0009 | Validated | Calculated Opportunity Score: 3.4
HGC-GAP-0042 | Marketing Copy | Horizontal | Correction of Website MCP Page Copy (Read/Write vs Read-Only) | FUNCTIONAL BUG | VERIFIED DEFECT / GAP | Verified current state in Marketing Copy: functionality missing, partial, or unoptimized. | Implementation of Correction of Website MCP Page Copy (Read/Write vs Read-Only) according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Correction of Website MCP Page Copy (Read/Write vs Read-Only) | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 3 | 3 | Small (1 day) | P1 | Implement Correction of Website MCP Page Copy (Read/Write vs Read-Only) per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Correction of Website MCP Page Copy (Read/Write vs Read-Only) with zero regression. | Automated integration tests and UI verification for HGC-GAP-0042 | Validated | Calculated Opportunity Score: 3.25
HGC-GAP-0035 | Study Abroad | Study Abroad | Automated Embassy Visa Appointment Slot Scraper Alert | AUTOMATION GAP | VALIDATED OPPORTUNITY | Verified current state in Study Abroad: functionality missing, partial, or unoptimized. | Implementation of Automated Embassy Visa Appointment Slot Scraper Alert according to global SaaS benchmarks. | Specialist Study Abroad CRMs | Benchmark equivalent for Automated Embassy Visa Appointment Slot Scraper Alert | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 5 | 4 | Medium (2 wks) | P2 | Implement Automated Embassy Visa Appointment Slot Scraper Alert per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Automated Embassy Visa Appointment Slot Scraper Alert with zero regression. | Automated integration tests and UI verification for HGC-GAP-0035 | Validated | Calculated Opportunity Score: 4.4
HGC-GAP-0016 | Insurance | Insurance | ACORD / IRDAI Standard Carrier Policy Statement Sync | INDUSTRY GAP | VALIDATED OPPORTUNITY | Verified current state in Insurance: functionality missing, partial, or unoptimized. | Implementation of ACORD / IRDAI Standard Carrier Policy Statement Sync according to global SaaS benchmarks. | Specialist Insurance CRMs | Benchmark equivalent for ACORD / IRDAI Standard Carrier Policy Statement Sync | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 5 | Large (3 wks) | P2 | Implement ACORD / IRDAI Standard Carrier Policy Statement Sync per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of ACORD / IRDAI Standard Carrier Policy Statement Sync with zero regression. | Automated integration tests and UI verification for HGC-GAP-0016 | Validated | Calculated Opportunity Score: 4.15
HGC-GAP-0020 | Travel Agencies | Travel | Live GDS Flight PNR Auto-Import (Amadeus/Sabre API) | INTEGRATION GAP | VALIDATED OPPORTUNITY | Verified current state in Travel Agencies: functionality missing, partial, or unoptimized. | Implementation of Live GDS Flight PNR Auto-Import (Amadeus/Sabre API) according to global SaaS benchmarks. | Specialist Travel CRMs | Benchmark equivalent for Live GDS Flight PNR Auto-Import (Amadeus/Sabre API) | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Large (3 wks) | P2 | Implement Live GDS Flight PNR Auto-Import (Amadeus/Sabre API) per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Live GDS Flight PNR Auto-Import (Amadeus/Sabre API) with zero regression. | Automated integration tests and UI verification for HGC-GAP-0020 | Validated | Calculated Opportunity Score: 4.0
HGC-GAP-0026 | Manufacturing | Manufacturing | Machine Capacity & Workstation Gantt Scheduling Calendar | INDUSTRY GAP | VALIDATED OPPORTUNITY | Verified current state in Manufacturing: functionality missing, partial, or unoptimized. | Implementation of Machine Capacity & Workstation Gantt Scheduling Calendar according to global SaaS benchmarks. | Specialist Manufacturing CRMs | Benchmark equivalent for Machine Capacity & Workstation Gantt Scheduling Calendar | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Large (3 wks) | P2 | Implement Machine Capacity & Workstation Gantt Scheduling Calendar per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Machine Capacity & Workstation Gantt Scheduling Calendar with zero regression. | Automated integration tests and UI verification for HGC-GAP-0026 | Validated | Calculated Opportunity Score: 4.0
HGC-GAP-0030 | Solar EPC | Solar | Rooftop Solar PV Irradiance & kWh Generation Estimator | INDUSTRY GAP | VALIDATED OPPORTUNITY | Verified current state in Solar EPC: functionality missing, partial, or unoptimized. | Implementation of Rooftop Solar PV Irradiance & kWh Generation Estimator according to global SaaS benchmarks. | Specialist Solar CRMs | Benchmark equivalent for Rooftop Solar PV Irradiance & kWh Generation Estimator | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Large (3-4 wks) | P2 | Implement Rooftop Solar PV Irradiance & kWh Generation Estimator per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Rooftop Solar PV Irradiance & kWh Generation Estimator with zero regression. | Automated integration tests and UI verification for HGC-GAP-0030 | Validated | Calculated Opportunity Score: 4.0
HGC-GAP-0033 | Digital Agencies | Agencies | Google Ads API Live Spend & ROAS Reporting Connector | INTEGRATION GAP | VALIDATED OPPORTUNITY | Verified current state in Digital Agencies: functionality missing, partial, or unoptimized. | Implementation of Google Ads API Live Spend & ROAS Reporting Connector according to global SaaS benchmarks. | Specialist Agencies CRMs | Benchmark equivalent for Google Ads API Live Spend & ROAS Reporting Connector | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Medium (2 wks) | P2 | Implement Google Ads API Live Spend & ROAS Reporting Connector per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Google Ads API Live Spend & ROAS Reporting Connector with zero regression. | Automated integration tests and UI verification for HGC-GAP-0033 | Validated | Calculated Opportunity Score: 4.0
HGC-GAP-0034 | Study Abroad | Study Abroad | International University Portal Application Tracker (UCAS/CommonApp) | INTEGRATION GAP | VALIDATED OPPORTUNITY | Verified current state in Study Abroad: functionality missing, partial, or unoptimized. | Implementation of International University Portal Application Tracker (UCAS/CommonApp) according to global SaaS benchmarks. | Specialist Study Abroad CRMs | Benchmark equivalent for International University Portal Application Tracker (UCAS/CommonApp) | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Large (3 wks) | P2 | Implement International University Portal Application Tracker (UCAS/CommonApp) per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of International University Portal Application Tracker (UCAS/CommonApp) with zero regression. | Automated integration tests and UI verification for HGC-GAP-0034 | Validated | Calculated Opportunity Score: 4.0
HGC-GAP-0043 | AI & Audio | Horizontal | Sub-5-Second Chunked Call Transcription & Action Extraction | PERFORMANCE GAP | VALIDATED OPPORTUNITY | Verified current state in AI & Audio: functionality missing, partial, or unoptimized. | Implementation of Sub-5-Second Chunked Call Transcription & Action Extraction according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Sub-5-Second Chunked Call Transcription & Action Extraction | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Medium (2 wks) | P2 | Implement Sub-5-Second Chunked Call Transcription & Action Extraction per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Sub-5-Second Chunked Call Transcription & Action Extraction with zero regression. | Automated integration tests and UI verification for HGC-GAP-0043 | Validated | Calculated Opportunity Score: 4.0
HGC-GAP-0013 | Healthcare / Clinic | Healthcare | US HIPAA BAA Enterprise Compliance Vault | SECURITY GAP | VALIDATED OPPORTUNITY | Verified current state in Healthcare / Clinic: functionality missing, partial, or unoptimized. | Implementation of US HIPAA BAA Enterprise Compliance Vault according to global SaaS benchmarks. | Specialist Healthcare CRMs | Benchmark equivalent for US HIPAA BAA Enterprise Compliance Vault | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 3 | 5 | Large (4 wks) | P2 | Implement US HIPAA BAA Enterprise Compliance Vault per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of US HIPAA BAA Enterprise Compliance Vault with zero regression. | Automated integration tests and UI verification for HGC-GAP-0013 | Validated | Calculated Opportunity Score: 3.95
HGC-GAP-0007 | Customer Support | Horizontal | Automated Multi-Tier SLA Escalation & Reassignment Actions | AUTOMATION GAP | VALIDATED OPPORTUNITY | Verified current state in Customer Support: functionality missing, partial, or unoptimized. | Implementation of Automated Multi-Tier SLA Escalation & Reassignment Actions according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Automated Multi-Tier SLA Escalation & Reassignment Actions | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Small (1 wk) | P2 | Implement Automated Multi-Tier SLA Escalation & Reassignment Actions per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Automated Multi-Tier SLA Escalation & Reassignment Actions with zero regression. | Automated integration tests and UI verification for HGC-GAP-0007 | Validated | Calculated Opportunity Score: 3.8
HGC-GAP-0008 | Invoicing & Commerce | Horizontal | Dedicated Credit Note & Partial Refund Modal Workflow | FEATURE GAP | VALIDATED OPPORTUNITY | Verified current state in Invoicing & Commerce: functionality missing, partial, or unoptimized. | Implementation of Dedicated Credit Note & Partial Refund Modal Workflow according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Dedicated Credit Note & Partial Refund Modal Workflow | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Medium (1-2 wks) | P2 | Implement Dedicated Credit Note & Partial Refund Modal Workflow per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Dedicated Credit Note & Partial Refund Modal Workflow with zero regression. | Automated integration tests and UI verification for HGC-GAP-0008 | Validated | Calculated Opportunity Score: 3.8
HGC-GAP-0025 | CA & Accounting | Accounting | Secure Client Document Upload Vault with Folder Permissions | SECURITY GAP | VALIDATED OPPORTUNITY | Verified current state in CA & Accounting: functionality missing, partial, or unoptimized. | Implementation of Secure Client Document Upload Vault with Folder Permissions according to global SaaS benchmarks. | Specialist Accounting CRMs | Benchmark equivalent for Secure Client Document Upload Vault with Folder Permissions | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Medium (2 wks) | P2 | Implement Secure Client Document Upload Vault with Folder Permissions per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Secure Client Document Upload Vault with Folder Permissions with zero regression. | Automated integration tests and UI verification for HGC-GAP-0025 | Validated | Calculated Opportunity Score: 3.8
HGC-GAP-0031 | Solar EPC | Solar | State DISCOM Net-Metering Document Template Generator | FEATURE GAP | VALIDATED OPPORTUNITY | Verified current state in Solar EPC: functionality missing, partial, or unoptimized. | Implementation of State DISCOM Net-Metering Document Template Generator according to global SaaS benchmarks. | Specialist Solar CRMs | Benchmark equivalent for State DISCOM Net-Metering Document Template Generator | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Small (1 wk) | P2 | Implement State DISCOM Net-Metering Document Template Generator per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of State DISCOM Net-Metering Document Template Generator with zero regression. | Automated integration tests and UI verification for HGC-GAP-0031 | Validated | Calculated Opportunity Score: 3.8
HGC-GAP-0039 | UI/UX & Shell | Horizontal | Responsive Slide-Over Contact Drawer on Tablet Viewports (<1200px) | UI/UX IMPROVEMENT | VALIDATED OPPORTUNITY | Verified current state in UI/UX & Shell: functionality missing, partial, or unoptimized. | Implementation of Responsive Slide-Over Contact Drawer on Tablet Viewports (<1200px) according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Responsive Slide-Over Contact Drawer on Tablet Viewports (<1200px) | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Small (3 days) | P2 | Implement Responsive Slide-Over Contact Drawer on Tablet Viewports (<1200px) per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Responsive Slide-Over Contact Drawer on Tablet Viewports (<1200px) with zero regression. | Automated integration tests and UI verification for HGC-GAP-0039 | Validated | Calculated Opportunity Score: 3.8
HGC-GAP-0045 | API & Webhooks | Horizontal | Outbound Webhook Exponential Backoff & Developer DLQ Console | PERFORMANCE GAP | VALIDATED OPPORTUNITY | Verified current state in API & Webhooks: functionality missing, partial, or unoptimized. | Implementation of Outbound Webhook Exponential Backoff & Developer DLQ Console according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Outbound Webhook Exponential Backoff & Developer DLQ Console | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 4 | Small (1 wk) | P2 | Implement Outbound Webhook Exponential Backoff & Developer DLQ Console per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Outbound Webhook Exponential Backoff & Developer DLQ Console with zero regression. | Automated integration tests and UI verification for HGC-GAP-0045 | Validated | Calculated Opportunity Score: 3.8
HGC-GAP-0036 | UI/UX & Shell | Horizontal | Customizable Pinned Sidebar Shortcuts & Vertical Switcher Dock | UI/UX IMPROVEMENT | VALIDATED OPPORTUNITY | Verified current state in UI/UX & Shell: functionality missing, partial, or unoptimized. | Implementation of Customizable Pinned Sidebar Shortcuts & Vertical Switcher Dock according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Customizable Pinned Sidebar Shortcuts & Vertical Switcher Dock | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 4 | 3 | Small (1 wk) | P2 | Implement Customizable Pinned Sidebar Shortcuts & Vertical Switcher Dock per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Customizable Pinned Sidebar Shortcuts & Vertical Switcher Dock with zero regression. | Automated integration tests and UI verification for HGC-GAP-0036 | Validated | Calculated Opportunity Score: 3.65
HGC-GAP-0004 | Marketing Campaigns | Horizontal | Multi-Touch Campaign Revenue Attribution Modeling | REPORTING GAP | VALIDATED OPPORTUNITY | Verified current state in Marketing Campaigns: functionality missing, partial, or unoptimized. | Implementation of Multi-Touch Campaign Revenue Attribution Modeling according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Multi-Touch Campaign Revenue Attribution Modeling | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 3 | 4 | Large (3-4 wks) | P2 | Implement Multi-Touch Campaign Revenue Attribution Modeling per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Multi-Touch Campaign Revenue Attribution Modeling with zero regression. | Automated integration tests and UI verification for HGC-GAP-0004 | Validated | Calculated Opportunity Score: 3.6
HGC-GAP-0019 | Real Estate | Real Estate | Embedded Matterport 3D Tour & Drone Video Viewer in Proposal | UI/UX IMPROVEMENT | VALIDATED OPPORTUNITY | Verified current state in Real Estate: functionality missing, partial, or unoptimized. | Implementation of Embedded Matterport 3D Tour & Drone Video Viewer in Proposal according to global SaaS benchmarks. | Specialist Real Estate CRMs | Benchmark equivalent for Embedded Matterport 3D Tour & Drone Video Viewer in Proposal | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 3 | 3 | 4 | Small (3 days) | P2 | Implement Embedded Matterport 3D Tour & Drone Video Viewer in Proposal per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Embedded Matterport 3D Tour & Drone Video Viewer in Proposal with zero regression. | Automated integration tests and UI verification for HGC-GAP-0019 | Validated | Calculated Opportunity Score: 3.55
HGC-GAP-0011 | Admin & Governance | Horizontal | Inline Record Drawer Field-Level Audit History Timeline | FEATURE GAP | VALIDATED OPPORTUNITY | Verified current state in Admin & Governance: functionality missing, partial, or unoptimized. | Implementation of Inline Record Drawer Field-Level Audit History Timeline according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Inline Record Drawer Field-Level Audit History Timeline | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 3 | 4 | Medium (2 wks) | P2 | Implement Inline Record Drawer Field-Level Audit History Timeline per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Inline Record Drawer Field-Level Audit History Timeline with zero regression. | Automated integration tests and UI verification for HGC-GAP-0011 | Validated | Calculated Opportunity Score: 3.4
HGC-GAP-0005 | Security & Admin | Horizontal | Exportable DPDP / GDPR Double Opt-In Audit Certificates | SECURITY GAP | VALIDATED OPPORTUNITY | Verified current state in Security & Admin: functionality missing, partial, or unoptimized. | Implementation of Exportable DPDP / GDPR Double Opt-In Audit Certificates according to global SaaS benchmarks. | Salesforce / HubSpot / Pipedrive | Benchmark equivalent for Exportable DPDP / GDPR Double Opt-In Audit Certificates | https://test.hellogrowthcrm.com | 2026-10-30 | HIGH | 4 | 3 | 3 | Small (1 wk) | P2 | Implement Exportable DPDP / GDPR Double Opt-In Audit Certificates per Section 2 architectural plans. | Supabase PostgreSQL / Edge Functions | Verified functionality of Exportable DPDP / GDPR Double Opt-In Audit Certificates with zero regression. | Automated integration tests and UI verification for HGC-GAP-0005 | Validated | Calculated Opportunity Score: 3.25

## Competitor Feature Matrix
Feature Pillar | HelloGrowth CRM ($12) | Salesforce Sales Cloud | HubSpot Sales Hub | Zoho CRM | Freshsales | Pipedrive | Close CRM | GoHighLevel | Bitrix24 | Attio CRM | LeadSquared
Visual Deal Pipelines | Yes (Unlimited) | Yes ($100+ Pro) | Yes ($100+ Pro) | Yes | Yes | Yes | Yes | Yes | Yes | Yes | Yes
Workflow Automation | Yes (Unlimited) | Yes (Tier Gated) | Locked to $100 Pro | Capped Rules | Tier Gated | Locked to $59 Pro | Yes ($49+) | Yes | Yes | Credit Metered | Locked to Super
Native WhatsApp Cloud API | Yes (2-Way Built-in) | 3rd Party Marketplace | 3rd Party Marketplace | 3rd Party / Add-on | Add-on | 3rd Party Only | 3rd Party Only | Twilio Markup | Native (Complex) | No | Yes (Add-on)
Built-in WebRTC VoIP Dialer | Yes (Included) | Add-on ($$$) | Paid Call Pack | Zoho Voice Add-on | Freshcaller Mins | No (3rd Party) | Yes (Core Focus) | Twilio Markup | Yes | No | Cloud Telephony Add-on
2-Way SMS Text Messaging | Yes (Included) | Add-on Pack | Locked to Pro | Add-on | Add-on | 3rd Party Only | Yes | Twilio Markup | Yes | No | Yes
Interactive Proposal Builder | Yes (Included) | CPQ Add-on ($75+) | Locked to Pro | Zoho Docs / Books | No | Smart Docs ($32/mo) | No | Yes | Yes | No | No
Digital E-Signatures | Yes (Included) | Add-on ($$$) | Locked to Pro | Zoho Sign | No | Smart Docs Add-on | No | Yes | Yes | No | No
Tax-Compliant Invoicing | Yes (GST & Sales Tax) | Billing Add-on | Stripe Add-on | Zoho Books Sync | No | Integration Only | No | Yes | Yes | No | No
AI Call Transcription & Summary | Yes (Included) | Agentforce ($$$) | Breeze AI ($$$) | Zia AI (Enterprise) | Freddy AI (Metered) | No | Yes ($109+) | Metered Add-on | CoPilot ($$$) | Call Intelligence ($79) | No
Human-in-the-Loop AI Approvals | Yes (Dedicated HUD) | No | No | No | No | No | No | No | No | No | No
Model Context Protocol (MCP) | Yes (77 Tools Live) | Documented Only | Documented Only | No | No | No | No | No | No | Public Docs MCP | No
Pre-built Industry Workspaces | Yes (33+ Verticals) | Force.com Custom | Custom Objects ($$$) | Zoho Creator ($$$) | No | No | No | Agency Sub-accounts | No | Custom Objects ($79) | Vertical Packs ($$$)
Mobile GPS Field Check-ins | Yes (Included) | Field Service ($$$) | No | Zoho FSM ($$$) | No | No | No | No | Basic Mobile | No | Yes (LeadSquared Field)
Client & Partner Self-Service Portal | Yes (8 Sub-views) | Experience Cloud ($$$) | Customer Portal ($$$) | Client Portal | Customer Portal | No | No | Client Portal | Extranet | Client Portal | Portal Add-on
Entry Plan List Price | $12 / user / mo | $25 / user / mo | $20 / user / mo | $20 / user / mo | $15 / user / mo | $24 / user / mo | $19 / user / mo | $97 / mo (3 users) | $49 / mo (5 users) | $35 / user / mo | $25 / user / mo
Mid-Tier / Standard Price | $12 / user / mo | $100 / user / mo | $95 / user / mo | $35 / user / mo | $39 / user / mo | $49 / user / mo | $49 / user / mo | $297 / mo flat | $99 / mo flat | $79 / user / mo | $60 / user / mo
Mandatory Onboarding Fee | $0 | $0 - $5,000 | $1,500 - $3,500 | $0 | $0 | $0 | $0 | $0 | $0 | $0 | $500 - $2,000

## Industry Comparison Matrix
Industry Vertical | Specialist Competitor Benchmarks | Core Process Requirements | HelloGrowth CRM Verified Capabilities | Identified Critical Gaps | Market Disruption Potential
Healthcare / Clinics | Practo Ray, Kareo, Athenahealth | EMR, Doctor OPD scheduling, e-prescriptions, lab tests, billing | ClinicDoctors, ClinicPatients, ClinicPrescriptions, ClinicVisits | DICOM/HL7 lab test file attachment parsing, US HIPAA BAA vault | High (Disrupts Practo's ₹2k/mo OPD software)
Education / Coaching | LeadSquared EdTech, Classpro, Teachmint | Student admissions, counseling follow-ups, fee installments, attendance | EduAdmissions, EduStudents, EduFees, EduAttendance, EduExams | Biometric device sync (ZKTeco/Essl), overdue fee WhatsApp bot | Very High (Matches LeadSquared at 80% lower cost)
Insurance Agencies | Applied Epic, AgencyBloc, Zoho Insurance | Policy tracking, renewal reminders, claims intake, commission splits | InsuranceDashboard, InsurancePolicies, InsuranceClaims, InsuranceCommissions | ACORD/IRDAI carrier statement sync, 1-click renewal WhatsApp payment | High (Cuts agency software overhead by 70%)
Real Estate Developers | Sell.Do, Follow Up Boss, Propertybase | Unit inventory matrix, site visit GPS, broker tracking, token payment | REDashboard, REUnits, RESiteVisits, REChannelPartners, RECollections | 30-min temporary unit holding lock, 3D Matterport tour embeds | Very High (Sell.Do charges ₹45k/mo setup)
Travel & Tour Agencies | Travefy, TravelWorks, Rezdy | Day-by-day itineraries, flight/hotel vouchers, supplier reconciliation | TravelAgencyDashboard, TravelBookings, TravelItineraryList, Packages | Live GDS flight PNR auto-import, offline traveler PWA caching | High (Replaces Travefy $49/mo standalone tool)
Retail & Point of Sale | Shopify POS, Lightspeed, Square | Rapid barcode checkout, receipting, stock transfers, customer loyalty | RetailDashboard, RetailPOSPage, RetailInventory, StockOperations | WebUSB/WebSerial direct ESC/POS thermal printing, offline IndexedDB | Very High (Replaces $89/mo POS hardware systems)
CA & Accounting Practices | TaxDome, Canopy, Karbon | GST/IT filing calendar, client document vault, audit notices, engagement | CaDashboard, CaFilingsPage, CaNoticesPage, CaCalendarPage | Government GSTN/IT portal live status sync, secure client upload vault | Very High (TaxDome charges $50/user/mo)
Manufacturing & Engineering | Katana Cloud Mfg, MRPEasy, Odoo Mfg | Bill of Materials (BOQ), work orders, machine scheduling, quality check | MfgDashboard, BoqView, MfgProductionHub, MfgQualityHub, DrawingsView | Machine capacity Gantt calendar, raw material stock shortage alerts | High (Bridges CRM and light shop-floor ERP)
Agri Inputs & Field Sales | FieldAssist, BeatRoute, Bizom | Rural dealer beat plans, secondary orders, agronomist farmer meetings | FieldSalesWorkspace, FieldVisitMap, RepTodayPage, DriversPage | Automated TSP beat route sequencing, distributor overdue credit lock | Very High (Direct alternative to FieldAssist/Bizom)
Solar EPC | Aurora Solar, OpenSolar, Scoop Solar | Rooftop solar sizing, BOQ components, DISCOM net-metering paperwork | BoqView, SiteExecutionView, DrawingsView, ClientApprovalsView | Rooftop PV irradiance estimator, state DISCOM document generator | High (Eliminates high-cost solar proposal tools)
Digital Marketing Agencies | GoHighLevel, AgencyAnalytics, DashClicks | Multi-client reporting, retainer billing, ad spend ROAS, approval portals | AgencyReportingPage, AgencyRetainersPage, MetaAdsAnalytics | Custom domain white-label portal sub-tenancy, Google Ads API connector | Very High (Competes directly with HighLevel $297/mo)
Study Abroad Consultancies | ApplyBoard, Adventus.io, Edvoy | University course finder, student visa checklist, application tracking | SabDashboard, SabStudentsPage, SabUniversitiesPage, SabApplications | International university portal sync, automated embassy slot alert | High (Replaces fragmented student agency sheets)

## Implementation Backlog
Priority | Gap ID | Module | Industry | Gap Title | Opportunity Score | Estimated Effort | Technical Risk | Key Action
P0 | HGC-GAP-0018 | Real Estate | Real Estate | Real Estate Temporary Unit Holding Lock (30-Min Token Hold) | 5 | Small (1 wk) | Low | Execute per Plan HGC-GAP-0018
P0 | HGC-GAP-0022 | Retail / POS | Retail | WebUSB/WebSerial Direct ESC/POS Thermal Receipt Printing | 4.65 | Medium (2 wks) | Low | Execute per Plan HGC-GAP-0022
P0 | HGC-GAP-0044 | Database & Perf | Horizontal | Compound B-Tree Indexes on High-Traffic Webhook & Activity Tables | 4.45 | Small (1 day) | Low | Execute per Plan HGC-GAP-0044
P0 | HGC-GAP-0010 | Security & Admin | Horizontal | Supabase Currency Settings Write Permission Vulnerability | 4.25 | Small (1 day) | Critical | Execute per Plan HGC-GAP-0010
P1 | HGC-GAP-0024 | CA & Accounting | Accounting | Government GSTN / Income Tax GSP Live Portal Status Sync | 5 | Large (3 wks) | Medium | Execute per Plan HGC-GAP-0024
P1 | HGC-GAP-0017 | Insurance | Insurance | Automated Policy Renewal Instant WhatsApp Payment Bot | 4.8 | Medium (2 wks) | Low | Execute per Plan HGC-GAP-0017
P1 | HGC-GAP-0023 | Retail / POS | Retail | Offline Cash Register Fallback with Local IndexedDB Sync | 4.8 | Large (3 wks) | Medium | Execute per Plan HGC-GAP-0023
P1 | HGC-GAP-0028 | Agri / Field Sales | Field Sales | Automated TSP Beat Route Sequencing for Rural Dealer Reps | 4.8 | Medium (2 wks) | Low | Execute per Plan HGC-GAP-0028
P1 | HGC-GAP-0032 | Digital Agencies | Agencies | Custom Domain White-Label Portal Sub-Tenancy | 4.8 | Medium (2 wks) | Low | Execute per Plan HGC-GAP-0032
P1 | HGC-GAP-0027 | Manufacturing | Manufacturing | Raw Material Stock Shortage Alert on Work Order Release | 4.65 | Medium (2 wks) | Low | Execute per Plan HGC-GAP-0027
P1 | HGC-GAP-0001 | Sales Pipeline | Horizontal | Enforced Pipeline Stage Gating & Required Stage Fields | 4.45 | Medium (2-3 wks) | Low | Execute per Plan HGC-GAP-0001
P1 | HGC-GAP-0029 | Agri / Field Sales | Field Sales | Distributor Overdue Credit Limit Gate Blocking New Orders | 4.45 | Small (1 wk) | Low | Execute per Plan HGC-GAP-0029
P1 | HGC-GAP-0015 | Education / Coaching | Education | Automated Overdue Fee Installment WhatsApp Drip Bot | 4.4 | Small (1 wk) | Low | Execute per Plan HGC-GAP-0015
P1 | HGC-GAP-0040 | AI & MCP | Horizontal | Official Model Context Protocol (MCP) Registry Listing | 4.4 | Small (2 days) | Low | Execute per Plan HGC-GAP-0040
P1 | HGC-GAP-0041 | AI & MCP | Horizontal | Standardized search/fetch Primitive Tools for HGC MCP Server | 4.25 | Small (3 days) | Low | Execute per Plan HGC-GAP-0041
P1 | HGC-GAP-0014 | Education / Coaching | Education | Hardware Biometric Device API Sync (ZKTeco/Essl) | 4.2 | Medium (2 wks) | Medium | Execute per Plan HGC-GAP-0014
P1 | HGC-GAP-0021 | Travel Agencies | Travel | Offline Mobile Traveler Itinerary PWA Caching | 4.2 | Small (1 wk) | Low | Execute per Plan HGC-GAP-0021
P1 | HGC-GAP-0037 | UI/UX & Shell | Horizontal | Sticky Left Column Pinning in Responsive Wide Data Tables | 4.2 | Small (3 days) | Low | Execute per Plan HGC-GAP-0037
P1 | HGC-GAP-0038 | UI/UX & Shell | Horizontal | Interactive Demo Sample Records Button on Empty State Views | 4.2 | Small (1 wk) | Low | Execute per Plan HGC-GAP-0038
P1 | HGC-GAP-0002 | Quotes & Commerce | Horizontal | Server-Side Discount Approval Thresholds (>15%) | 4 | Medium (2 wks) | Low | Execute per Plan HGC-GAP-0002
P1 | HGC-GAP-0003 | Lead Management | Horizontal | Fuzzy & Probabilistic Lead Deduplication Engine | 4 | Medium (2 wks) | Medium | Execute per Plan HGC-GAP-0003
P1 | HGC-GAP-0006 | Customer Support | Horizontal | Cross-Channel Conversation Thread Auto-Merging (WA + Email + Portal) | 4 | Medium (2 wks) | Medium | Execute per Plan HGC-GAP-0006
P1 | HGC-GAP-0012 | Healthcare / Clinic | Healthcare | Diagnostic Lab Report & DICOM/HL7 Attachment Parsing | 4 | Large (3 wks) | Medium | Execute per Plan HGC-GAP-0012
P1 | HGC-GAP-0009 | Payments & Billing | Horizontal | PayU Payment Gateway Discrepancy (Backend Missing) | 3.4 | Small (3 days) | Low | Execute per Plan HGC-GAP-0009
P1 | HGC-GAP-0042 | Marketing Copy | Horizontal | Correction of Website MCP Page Copy (Read/Write vs Read-Only) | 3.25 | Small (1 day) | Low | Execute per Plan HGC-GAP-0042